## Slide 1: Digital learning transformation: Phase 2 readout
Steering committee briefing (illustrative example data)
June 2026
Status report

## Slide 2
Where we stand after six months

## Slide 3: Phase 2 is on track: adoption and satisfaction exceed targets
Program scorecard
Source: TETP program office (illustrative)
82%
+14 pts vs target
Platform adoption across academies
4.4/5
+0.6 vs baseline
Learner satisfaction
37
of 45 planned
Courses migrated to new platform
SAR 2.1M
+12% vs plan
Run-rate savings identified

## Slide 4: Three forces will shape the next phase of the program
Source: TETP analysis (illustrative)
01
AI-assisted instruction
Adaptive tutoring pilots cut time-to-competency by 23% in two academies; scaling requires instructor enablement.
02
Capacity constraints
Instructor availability is the binding constraint for FY27 expansion; certification pipeline covers only 60% of demand.
03
Funding window
The transformation budget envelope closes in Q2 FY27; uncommitted scope must be locked by December.

## Slide 5: Centralized delivery outperforms the federated model on every cost metric
Operating model assessment
Source: TETP benchmarking (illustrative)
Centralized academy model
• One shared platform team; 11 FTE total
• Cost per learner-hour of SAR 38
• Single content pipeline, 4-week turnaround
• Consistent quality assurance across academies
Federated model (status quo)
• Five parallel platform teams; 19 FTE total
• Cost per learner-hour of SAR 61
• Duplicate content builds across academies
• Quality varies; no shared standards

## Slide 6: A four-step path takes the program from pilot to full scale
Source: TETP program office (illustrative)
Scale-up approach
Consolidate
• Merge platform teams and standardize toolchain by Q3.
Certify
• Run instructor certification waves; 120 instructors by Q4.
Migrate
• Move remaining 8 courses; retire legacy systems.
Scale
• Onboard three remaining academies in FY27.

## Slide 7: Key decisions cluster in the next two quarters
Source: TETP program office (illustrative)
Program milestones
Jul 2026
Operating model decision
Sep 2026
Instructor wave 2 complete
Dec 2026
Scope lock for FY27
Mar 2027
Legacy platform retired
Jun 2027
All academies onboarded

## Slide 8: Adoption growth is driven by the three largest academies
Monthly active learners by academy cluster
Source: Platform analytics, May 2026 (illustrative)
Key takeaways
• Large academies added 4,700 active learners in five months
• Specialist units lag; targeted onboarding starts in July
• Growth rate supports the FY27 scale-up case
Chart: 
| Jan | Feb | Mar | Apr | May
Large academies | 4200 | 5100 | 6300 | 7600 | 8900
Mid-size academies | 2100 | 2300 | 2700 | 3000 | 3400
Specialist units | 800 | 900 | 1000 | 1200 | 1300

## Slide 9: Course migration is ahead of plan in three of five academies
Source: TETP program office, June 2026 (illustrative)
Migration status by academy
Academy | Courses planned | Migrated | On plan? | Go-live
Naval Academy | 12 | 11 | Yes | Q3 FY26
Technical Institute | 10 | 9 | Yes | Q3 FY26
Aviation School | 8 | 7 | Yes | Q4 FY26
Logistics College | 9 | 6 | At risk | Q1 FY27
Medical Training Center | 6 | 4 | At risk | Q1 FY27

## Slide 10: Delivery setup is on track to support pilot delivery from September
Source: TETP program office (illustrative)
Workstream status
Output
Progress Update
Course Delivery Setup
Conduct student selection
– Drafted student selection criteria with service institutes
Secure approval to launch the pilot courses
– Started preparing the Training Authorization Document
Select instructors for the pilot courses
– Defined instructor selection criteria; two nominations requested per institute
Set up LMS and digital course materials
– Not started
Prepare the physical delivery setup
– Not started
Not Started
On Track
Completed

## Slide 11: Risks are manageable if two decisions land on time
Top risks
Mitigations in motion
Instructor pipeline shortfall in FY27
Legacy contract auto-renews in January
Content quality drift across academies
Certification wave 2 doubled in size
Termination notice drafted for legal review
Shared QA rubric pilots this quarter
Source: TETP risk register (illustrative)

## Slide 12: Ask of the committee: three approvals to keep Phase 2 on schedule
Source: TETP program office (illustrative)
Next steps
• Approve the centralized operating model effective Q3 FY26
  – Consolidates five platform teams into one; saves SAR 4.2M over two years
• Commit FY27 scope by December to stay inside the funding window
  – Unfunded scope defaults to FY28 with materially higher unit costs
• Endorse instructor certification wave 2 starting September
  – 120 instructors certified by year-end closes the capacity gap